## Slide 1
aspice-audit-master-edge-extension
三周开发甘特图 | 2026/07/23 - 2026/08/14 | Leadership report view
目标：完成 Helix 联动稳定化、Codex 审核增强、正式报告输出与试点发布
Kickoff
Week 1: Baseline & Helix Fix
Week 2: Audit Intelligence
Week 3: Pilot Release
Workstream / Deliverable
7/23 Thu
7/24 Fri
7/27 Mon
7/28 Tue
7/29 Wed
7/30 Thu
7/31 Fri
8/3 Mon
8/4 Tue
8/5 Wed
8/6 Thu
8/7 Fri
8/10 Mon
8/11 Tue
8/12 Wed
8/13 Thu
8/14 Fri
PM / Scope control
范围冻结、里程碑、领导汇报节奏
Kickoff
M1
M2
M3
Home UX & plugin shell
首页复原、Helix 下沉、语言/下载/登录体验
Home UX
Review
Helix ALM integration
项目读取、REQ/RE/issues/TASK、100 条采样、失败回退
REST + expand fix
Evidence picker
Evidence library & ASPICE mapping
SYS/SWE/SUP/MAN 分类、BP/GP 证据网格、文件依赖
Mapping rules
Calibration
Codex review intelligence
过程域锁定、完整证据输入、结构化建议、评分候选
Prompt + scoring
Formal report / PDF
VW 样式报告、证据引用、分数与关闭计划
Report template
Security & local bridge
密码会话暂存、CORS、ExecutionPolicy、打包脚本
Bridge hardening
Security check
Real project UAT
CEP-LP XiaoPeng / CDD 样本、审核员反馈、缺陷关闭
Pilot UAT
Release package & demo
CRX/ZIP、安装说明、领导演示材料
v1.7 release
M1 v1.5 Demo
M2 Pilot Go/No-Go
M3 v1.7 Release
Week 2 目标：Codex 建议页能基于 Helix + 上传证据输出 BP/GP 候选和项目问题点
Week 3 目标：真实项目 UAT 完成，输出可安装插件包、PDF 报告样张和领导演示材料
关键依赖
• Helix REST 网络与账号权限稳定；CEP-LP XiaoPeng / CDD 样本可持续访问。
• Codex bridge 按企业配置运行，避免模型/认证变更影响审核页。
• 每周五形成可演示版本，领导评审后锁定下一周范围，避免功能蔓延。
Confidential